## Tips for Planning
These are based in Mitch Lacey (MC) original instructions
Project Preparation
1. Fill in the Team Roster, specially the alias that will be used in the other sheets. The alias should not be changed once used in the other sheets.
MC also recomends to fill in the Sprint Vision (Team Roster!$C$4) so its clear for all members of the team.
2. Set the sprint start date in Capacity!$E$3 (this template version allows future dates)
3. Specify your options for the project in Analysis!E54:E55 (gray cells)
a. SkipWeekends (Analysis!E54) - 0 = 30 days calendar; 1 = 30 working days. Do not switch after Sprint has started or data will be stored under wrong days.
4. Specify team capacity along the sprint in Capacity
a. This template has 40 days please hide the unnecessary days (columns) starting on the right. (select the columns using the mouse cursor, right click and select Hide). Please do not delete columns.
b. Fill in every team member capacity. You have two options:
i. If there is a constant capacity you should use % allocation instead of hours and set all days to 8H
ii. If there isn't a constant capacity you should use % allocation=100% and set the hours in the table from 0 to 8.
c. Signal Hollidays, Off time and other activities as indicated in Capacity!K29:K31
d. Capacity!B9:C11 show if the capacity is enough or exceds the current left effort. This requires that all task's responsibles are filled in. (see ATTENTION)
Yellow signals under use of resources; red, over use
Sprint Planning
5. Fill in the Sprint Backlog items in Sprint
a. This template has 40 days. You can hide the unecessary days (columns) starting on the right. (select the columns using the mouse cursor, right click and select Hide). Please do not delete columns.
b. You have the following columns:
i. Worktype - select between Feature, Tax, Precondition or Spike.
Feature - tasks regarding functionality that will be valuable to the user
Tax - tasks regarding cost of doing business (in this case because of SCRUM)
Precondition - tasks that must happen at the completion (for instance to guarantee quality - eg: code review)
Spike - tasks regarding brief experiments to learn more about na area.
ii. Delivery Area
iii. Product Backlog Item or User Story
iv. Product Backlog Item or User Story ID
v. Task - Sprint Work item Description
vi. Responsible - mandatory - fill in with "no one" if it is not yet assigned
c. Weekend columns are signaled. If you decided to SkipWeekends, weeks will be separated by light orange lines.
d. To insert a new row, copy & paste an existing row. To select na entire row click in the row number on the left. Copy and paste it.
6. Verify if the Timesheet AddIn is well configured in Sprint!$F2:$F3. The timesheet AddIn allows to import project hours already reported to SharePoint. To install this AddIn please ask for more information.
If F and G columns are not visible, plese unhide them.
a.TimesheetList2017 references the SharePoint List that keeps Timesheets from 2017. (You should change year if you are in a different year)
b. Fill in [Timesheet Project Code] with your project code that appears in the Timesheet exactly as it is there.
Analysis & Charts
7. Analyse your sprint performance in Analysis sheets
a.This template has 40 days. You can hide the unecessary days (columns) starting on the right. (select the columns using the mouse cursor, right click and select Hide). Please do not delete columns.Once you hide the unecessary columns your charts will instantaneously adapt to the sprint duration.
b. You can change burndown legend labels in Analysis!A1:A23 (gray cells)
c. To remenber how you read burndowns
i. If Current Remaining is bellow Planned Remaining it means that the team is going faster than expected
ii. If Current Remaining is equal to Planned Remaining it means that the team is going as expected
iii. If Current Remaining is above Planned Remaining it means that the team is going slower than expected
iv. If Current Spent is bellow Planned Capacity it means that the team is working less time in the project that expected
v. If Current Spent is equal to Planned Capacity it means that the team is working as planned
vi. If Current Spent is above Planned Capacity it means that the team is working longer in the project than expected
vii. If the blue surface increases along the sprint it means that the scope has increased or that the effort that was initially planned was not enough

## Tips for Daily
These are based in Mitch Lacey (MC) original instructions
Report Progress & Assign tasks - every day
1. All team members must previously report the time spent in the project tasks in the Timesheet and syncronize w/ SharePoint using Reporte Horas > Reportar.
a. You should use the task descriptions as they are in the sprint backlog. We suggest you to copy paste it.
2. Every day, beforey daily scrum, import all reported hours to the Sprint Backlog using the TimeSheet AddIn.
a. If you don't have the Add In yet please do the following: Insert > My Add-ins (in Add-ins); See All and then My Organization; Select GetScrumData from CreateIT
b. You must logged in using your common credentials @ O365
c. Add-In options Get Week or day require that you previously select the day
d. Analyse the tasks that the AddIn reports as not beeing yet in the sprint backlog.
3. During daily Scrum each team mumber must update the sprint backlog:
a. In the previous day review the effort that you think is necessary to conclude (Left column). Previous days or weekends are signaled with a dotter pattern.
b. Change the responsible cell in all newly assigned tasks. You can check if the capacity is under or over used in Capacity sheet.
Analysis & Charts
3. Analyse your sprint performance in Analysis or Charts sheets
a. To remember how you read burndowns
i. If Current Remaining is bellow Planned Remaining it means that the team is going faster than expected
ii. If Current Remaining is equal to Planned Remaining it means that the team is going as expected
iii. If Current Remaining is above Planned Remaining it means that the team is going slower than expected
iv. If Current Spent is bellow Planned Capacity it means that the team is working less time in the project that expected
v. If Current Spent is equal to Planned Capacity it means that the team is working as planned
vi. If Current Spent is above Planned Capacity it means that the team is working longer in the project than expected
vii. If blue surface increases along the sprint it meand that the scope has increased or that effort that was initially planned was not enough

## Sprint
Project: [Easy Chair]
[5 empty] | TimesheetList2017 | 2.3
|  | Sprint [x] - [Sprint Goal] |  |  | [Timesheet Project Code]
[9 empty] | Start Date | 2018-04-24 |  |  | 2018-04-24 |  |  | 2018-04-25 |  |  | 2018-04-26 |  |  | 2018-04-27 |  |  | 2018-04-28 |  |  | 2018-04-29 |  |  | 2018-04-30 |  |  | 2018-05-01 |  |  | 2018-05-02 |  |  | 2018-05-03 |  |  | 2018-05-04 |  |  | 2018-05-05 |  |  | 2018-05-06 |  |  | 2018-05-07 |  |  | 2018-05-08 |  |  | 2018-05-09 |  |  | 2018-05-10 |  |  | 2018-05-11 |  |  | 2018-05-12 |  |  | 2018-05-13 |  |  | 2018-05-14 |  |  | 2018-05-15 |  |  | 2018-05-16 |  |  | 2018-05-17 |  |  | 2018-05-18 |  |  | 2018-05-19 |  |  | 2018-05-20 |  |  | 2018-05-21 |  |  | 2018-05-22 |  |  | 2018-05-23 |  |  | 2018-05-24 |  |  | 2018-05-25 |  |  | 2018-05-26 |  |  | 2018-05-27 |  |  | 2018-05-28 |  |  | 2018-05-29 |  |  | 2018-05-30 |  |  | 2018-05-31 |  |  | 2018-06-01 |  |  | 2018-06-02 |  |  | Spent Effort |  | Left Effort |  | Total Effort |  | Deviation
[11 empty] | Priority | Initial Effort | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4 |  |  | Day 5 |  |  | Day 6 |  |  | Day 7 |  |  | Day 8 |  |  | Day 9 |  |  | Day 10 |  |  | Day 11 |  |  | Day 12 |  |  | Day 13 |  |  | Day 14 |  |  | Day 15 |  |  | Day 16 |  |  | Day 17 |  |  | Day 18 |  |  | Day 19 |  |  | Day 20 |  |  | Day 21 |  |  | Day 22 |  |  | Day 23 |  |  | Day 24 |  |  | Day 25 |  |  | Day 26 |  |  | Day 27 |  |  | Day 28 |  |  | Day 29 |  |  | Day 30 |  |  | Day 31 |  |  | Day 32 |  |  | Day 33 |  |  | Day 34 |  |  | Day 35 |  |  | Day 36 |  |  | Day 37 |  |  | Day 38 |  |  | Day 39 |  |  | Day 40 |  |  |  |  | Left Effort |  | Total Effort
Worktype | Deliverable area | PB Item or User Story | Depende Design | Actividade do processo | PB Item ID | Work item ID | Tecnologia | Task | Responsible | Status |  | Initial Effort | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Hours | Days | Hours | Days | Hours | Days | Rate | Abs. Hours | Abs. Days
Feature | Specification | User Story 1 | [5 empty] | Elicitação Reqs. Identificar Goals | MA | Complete |  | 4 | 4 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 4 | 0.5 | 0 | 0 | 4 | 0.5 | 0% | 0 | 0
Feature | Specification | User Story 2 | [5 empty] | Elicitação Reqs. Identificar Agents | MR | Complete |  | 4 | 0 | 4 | To start | 4 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 4 | 0.5 | 0 | 0 | 4 | 0.5 | 0% | 0 | 0
Feature | Specification | [6 empty] | Elicitação Reqs. Definição Non-Funct. Goals | JQ | Complete |  | 4 | 0 | 4 | To start | 0 | 0 | Complete | 4 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 4 | 0.5 | 0 | 0 | 4 | 0.5 | 0% | 0 | 0
Feature | Specification | [6 empty] | Elicitação Reqs. Identificar Obstaculos e Resolução | MA | Complete |  | 4 | 0 | 4 | To start | 0 | 0 | Complete | 0 | 0 | Complete | 4 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 4 | 0.5 | 0 | 0 | 4 | 0.5 | 0% | 0 | 0
Feature | Specification | [6 empty] | Elicitação Reqs. Identiciar Objectos e Operações | MA | Complete |  | 4 | 0 | 4 | To start | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 4 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 4 | 0.5 | 0 | 0 | 4 | 0.5 | 0% | 0 | 0
Feature | Specification | [6 empty] | Análise de Reqs. Escolher Parafigma Orientado a Objectos | MA | Complete |  | 4 | 0 | 4 | To start | 0 | 4 | To start | 0 | 4 | To start | 0 | 4 | To start | 0 | 4 | To start | 4 | 0 | Complete | 0 | 0 | Complete | 8 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 12 | 1.5 | 0 | 0 | 12 | 1.5 | 200% | 8 | 1
Feature | Development | [6 empty] | Mapear Modelo de Reqs. - Modelo de Use Cases | MA | Complete |  | 4 | 0 | 0 | Complete | 0 | 0 | Complete | 8 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 4 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 12 | 1.5 | 0 | 0 | 12 | 1.5 | 200% | 8 | 1
Feature | Development | [6 empty] | Mapear Modelo de Reqs. - Selecionar 6 Uses Cases |  | Complete |  | 4 | 0 | 4 | To start | 0 | 4 | To start | 0 | 4 | To start | 0 | 4 | To start | 0 | 4 | To start | 0 | 4 | To start | 0 | 4 | To start | 4 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 4 | 0.5 | 0 | 0 | 4 | 0.5 | 0% | 0 | 0
Feature | Development | [6 empty] | Mapear Modelo de Reqs. -Definir uma User Story para Use Cases |  | Complete |  | 2 | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 2 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 2 | 0.25 | 0 | 0 | 2 | 0.25 | 0% | 0 | 0
Feature | Development | [6 empty] | Mapear Modelo de Reqs. -Diagrama de classes |  | Complete |  | 2 | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 0 | 2 | To start | 2 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 2 | 0.25 | 0 | 0 | 2 | 0.25 | 0% | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | Undefined |  | 0 | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | Undefined | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[13 empty] | Day |  | 1 | Day |  | 2 | Day |  | 3 | Day |  | 4 | Day |  | 5 | Day |  | 6 | Day |  | 7 | Day |  | 8 | Day |  | 9 | Day |  | 10 | Day |  | 11 | Day |  | 12 | Day |  | 13 | Day |  | 14 | Day |  | 15 | Day |  | 16 | Day |  | 17 | Day |  | 18 | Day |  | 19 | Day |  | 20 | Day |  | 21 | Day |  | 22 | Day |  | 23 | Day |  | 24 | Day |  | 25 | Day |  | 26 | Day |  | 27 | Day |  | 28 | Day |  | 29 | Day |  | 30 | Day |  | 31 | Day |  | 32 | Day |  | 33 | Day |  | 34 | Day |  | 35 | Day |  | 36 | Day |  | 37 | Day |  | 38 | Day |  | 39 | Day |  | 40
[8 empty] | Time Spent Mask |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
[8 empty] | Time Left Mask |  |  |  |  | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0
[8 empty] | Status Mask |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1
[8 empty] | Total: |  |  | (hours) | 36 | 4 | 0 |  | 4 | 12 |  | 0 | 12 |  | 4 | 12 |  | 4 | 12 |  | 4 | 8 |  | 4 | 8 |  | 14 | 2 |  | 0 | 2 |  | 2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 6.5 | 0 | 0 | 52 | 6.5 | 44.44% | 52 | 6.5
[11 empty] | (days) | 4.5 | 0.5 | 0 |  | 0.5 | 1.5 |  | 0 | 1.5 |  | 0.5 | 1.5 |  | 0.5 | 1.5 |  | 0.5 | 1 |  | 0.5 | 1 |  | 1.75 | 0.25 |  | 0 | 0.25 |  | 0.25 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team Roster
Sprint Vision | [Sprint Vision]
Sprint Team | Name | Initial | Phone | Mobile phone | Email | IM
| Team | Team
| Miguel Almeida | MA
| Miguel Rosa | MR
| João Albuquerque | JQ
| No one | No one

## Capacity
Current Date |  |  | Wed | 2018-05-30
Sprint Start Date |  |  | Tue | 2018-04-24
Capacity Tracking Stats | [7 empty] | Team Member Available Capacity (Hours)
[8 empty] | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | Available Capacity |  |  | Available Capacity -Assigned Effort
|  |  |  | Project Team | % Allocation | Assigned Hours | Assigned Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | Hours |  | Days | Hours | Days
| Hours | Days |  | MA | 100% | 36 | 4.5 | 8 | 8 | 8 | 0 |  |  | 0 | 8 | 8 | 8 | 0 |  |  | 0 | 8 | 8 | 8 | 0 |  |  | 0 | 8 | 8 | 8 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 96 |  | 12 | 60 | 7.5
Total Capacity | 116 | 14.5 |  | C2 | 100% | 0 | 0 | 8 | 4 | 8 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 20 |  | 2.5 | 20 | 2.5
Planned Effort | 36 | 4.5 |  | C3 | 100% | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
Total Effort (Spent + Remaining) | 36 | 4.5 |  | C4 | 100% | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
Total Effort - Capacity | 80 | 10 |  | C5 | 100% | 0 | 0 | 0 | H | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
ATTENTION | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
The responsible must be fullfilled in all sprint |  |  |  | Team | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
tasks. Use "No one" instead of null. |  |  |  | No one | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
Yellow = Under use | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
Red = Over use | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | Total |  | 16 | 12 | 16 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 0 | 14.5
[6 empty] | Accumulated |  | 16 | 28 | 44 | 44 | 44 | 44 | 44 | 52 | 60 | 68 | 68 | 68 | 68 | 68 | 76 | 84 | 92 | 92 | 92 | 92 | 92 | 100 | 108 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116
[8 empty] | H | = | Holidays
[8 empty] | OFF | = | OFF
[8 empty] | OA | = | Other activities

## Analysis
Date |  | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02
Calendar Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Current Remaining |  | 28 | 12 | 12 | 12 | 12 | 8 | 8 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A
Current Spent in Day |  | 4 | 4 | 12 | 4 | 4 | 4 | 4 | 14 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A
Current Spent |  | 4 | 8 | 20 | 24 | 28 | 32 | 36 | 50 | 50 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | #N/A | #N/A | #N/A
Estimated Remaining + Spent |  | 32 | 20 | 32 | 36 | 40 | 40 | 44 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | #N/A | #N/A | #N/A
Forecast Remaining |  | 28 | 12 | 12 | 12 | 12 | 8 | 8 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8.6759 | -9.2207 | -9.7655 | -10.3103
Planned Remaining |  | 20 | 8 | -8 | -8 | -8 | -8 | -8 | -16 | -24 | -32 | -32 | -32 | -32 | -32 | -40 | -48 | -56 | -56 | -56 | -56 | -56 | -64 | -72 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80 | -80
Planned Capacity |  | 16 | 28 | 44 | 44 | 44 | 44 | 44 | 52 | 60 | 68 | 68 | 68 | 68 | 68 | 76 | 84 | 92 | 92 | 92 | 92 | 92 | 100 | 108 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116
Average Spent Per Day |  | 4 | 4 | 6.6667 | 6 | 5.6 | 5.3333 | 5.1429 | 6.25 | 5.5556 | 5.2 | 4.7273 | 4.3333 | 4 | 3.7143 | 3.4667 | 3.25 | 3.0588 | 2.8889 | 2.7368 | 2.6 | 2.4762 | 2.3636 | 2.2609 | 2.1667 | 2.08 | 2 | 1.9259 | 1.8571 | 1.7931 | 1.7333 | 1.6774 | 1.625 | 1.5758 | 1.5294 | 1.4857 | 1.4444 | 1.4054 | #N/A | #N/A | #N/A
Estimated Completion Date (based in Avg Spent By Day) |  | 2018-05-01 | 2018-04-28 | 2018-04-27 19:12 | 2018-04-29 | 2018-04-30 03:26 | 2018-04-30 12:00 | 2018-05-01 13:20 | 2018-05-01 07:41 | 2018-05-02 08:38 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | #N/A | #N/A | #N/A
Estimated Completion Date (based in Avg Task completion) |  | 2018-04-25 | 2018-04-24 06:00 | 2018-04-26 | 2018-04-27 12:00 | 2018-04-29 06:00 | 2018-04-28 10:55 | 2018-04-30 | 2018-05-01 07:41 | 2018-05-02 08:38 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | #N/A | #N/A | #N/A
Tasks Hours
To start |  | 28 | 12 | 12 | 12 | 12 | 8 | 8 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A
Running |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A
Complete |  | 16 | 32 | 32 | 32 | 32 | 44 | 44 | 50 | 50 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | #N/A | #N/A | #N/A
Count of Tasks
To start |  | 8 | 4 | 4 | 4 | 4 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A
Running |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A
Complete |  | 2 | 6 | 6 | 6 | 6 | 7 | 7 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | #N/A | #N/A | #N/A
Workbook Settings |  | 2018-04-26: Comments
| SkipWeekends | 2018-04-24: 0; 2018-04-26: (0=30 calendar days; 1=30 working days). Set to 1 to have dates skip over weekends (30 working day sprint, >30 calendar day sprint). Do not switch after Sprint has started or data will be stored under wrong days
| DailyScrumDateModifier | 2018-04-24: 0; 2018-04-26: Number of days added to or subtracted from today's date to ensure the highlighted date column in the sprint worksheet corresponds to the day of the current daily Scrum meeting
Workbook-Wide Constants
| BurndownColumns | 2018-04-24: 3
HoursSpentColumn | bar: 2018-04-24
| HoursLeftColumn | 2018-04-24: 2
| StatusColumn | 2018-04-24: 3
Note on A13: Autor: Current Spent / Number of Days
Note on A14: Autor: Hoje + Estimated Remaining/AvgSpentPerday
Note on A15: Autor: Hoje + (Estimated RemainingAndLeft*NrDays/Hours_Complete-1)

## Project Report
Work Type Breakdown | Count | Hours Sum | % Hours
Feature | 10 | 52 | 100%
Tax | 0 | 0 | 0%
Precondition | 0 | 0 | 0%
Spike | 0 | 0 | 0%
Total | 10 | 52 | 100%
Functional Breakdown | Count | Hours Sum | % Hours
Management | 0 | 0 | 0%
Specification | 6 | 32 | 61.54%
Development | 4 | 20 | 38.46%
Documentation | 0 | 0 | 0%
Training | 0 | 0 | 0%
Acceptance | 0 | 0 | 0%
Go live | 0 | 0 | 0%
Total | 10 | 52 | 100%
Work Item Status | Count | Hours Sum | % Hours
Complete | 10 | 52 | 100%
To Start | 0 | 0 | 0%
Running | 0 | 0 | 0%
Posponed | 0 | 0 | 0%
Cancelled | 0 | 0 | 0%
Total | 10 | 52 | 100%